## Sheet1
Sprint | Feature Set / Requirements ID | Topic | User Story | Task # | Task | Priorities | Assigned To | Start Date | End Date | Hours(Task Based)Estimate the testing+development-Technical Panel | Story Point(Bussiness Value/Complexity)Estimate how much we can deliver in a sprint+total efford with its task with its risk dependencies and other Factors(Pro+Scrum) | Status | Short Description of Feature Set/ Feature | Dependency of Feature Set/ Feature | Feature Owner | Feature Complexity | Business Priority | Feature Type | Remarks
1 | FS 1 / Req_1 and 2 | User Registration | As an user, I want to open user registration page and save the entered user details. | Task#1 | Create a Login JSP page to accept UserId and Password and allow to login and provide with registration link. | High | Prachi | 28/3/19 | 28/3/19 | 6 | M | Completed | The objective of this requirement is to allow the admin to Register as a new admin and redirect to new admin registration form. | Admin being able to access the homepage & get redirected to the ‘Admin Registration’ page upon click of ‘New User?’ link. | Scrum Master | Average | High | New Requirement
|  |  |  | Task#2 | Create a jsp pageand redirect to user Registration Page | High | Rohini | 28/3/19 | 29/3/19 | 6 | L | Completed |  |  | Scrum Master | Average | High | New Requirement
|  |  |  | Task#3 | User Registration Field Validation | Medium | Prachi | 29/3/19 | 29/3/19 | 6 | L | Completed |  |  | Scrum Master | Average | High | New Requirement
|  |  |  | Task#4 | Submit the data and store it in the database | High | Rohini | 29/3/19 | 29/3/19 | 6 | M | Completed |  | dependented on task 1 ,2 and 3 | Scrum Master | Average | High | New Requirement
|  |  |  | Task#5 | Create User Entity class, User DAO and User Service class to insert the admin data and controller and verify on backend. | High | Prachi | 29/3/19 | 30/3/19 | 6 | M | Completed | The objective of this module is to load the HR page where lot of HR fuctionalities are there where HR will take care of complete process of schedule an interview for a candidate. |  | Scrum Master | Average | High | New Requirement
|  |  |  | Task#6 | Successful login | High | Pranay | 29/3/19 | 30/3/19 | 6 | L | Completed |  |  | Scrum Master | Average | High | New Requirement
| FS 1 / Req_3and 4 | HR Home | As an HR, I want to land on HR Home page which will display all the HR Functionalities from the database | Task#7 | Create a jsp page for HR Home and successfully land on it after validating credentials. | High | Prachi | 31/03/19 | 31/03/19 | 6 | M | Completed |  |  | Scrum Master | Average | High | New Requirement
|  |  |  | Task#8 | Fetch all the details from the database by creating candidate class, DAO, Service and controller | High | Rohini | 31/03/19 | 2019-01-04 | 6 | M | Completed |  |  | Scrum Master | Average | High | New Requirement
|  |  |  | Task#9 | Create a ' Candidate requirement' and redirect to Add Candidate RequirementPage and submit the details in the database. | High | Rohini | 2019-02-04 | 2019-02-04 | 6 | S | Completed |  |  | Scrum Master | Average | High | New Requirement
|  |  |  | Task#10 | Edit candidate details by updating it in the database using the requirement id . | High | Prachi | 2019-03-04 | 2019-04-04 | 6 | M | Completed |  |  | Scrum Master | Average | High | New Requirement
|  |  |  | Task#11 | Schedule interview by redirecting to Schedule Interview Page. |  | Pranay | 2019-05-04 | 2019-06-04 | 6 | M | Completed |  |  | Scrum Master | Average | High | New Requirement
|  |  |  | Task#12 | provide interview results of different candidates by redirecting it to Interview Observation page. | High | Rohini | 2019-06-04 | 2019-06-04 | 6 | M | Completed |  |  | Scrum Master | Average | High | New Requirement
3 | FS 2 / Req_5 and 6 | Candidate Home | As an candidate, I want to land on Candidate Home page which will display all the details from the database | Task#13 | Create a jsp page for Candidate Home and successfully land on it after validating credentials. | High | Prachi | 2019-06-04 | 2019-06-04 | 6 | S | Completed | The main objective of this page is to load the candidate login home page for filling candidate details in the databse. |  | Scrum Master | Average | High | New Requirement
|  |  |  | Task#14 | Fetch all the details from the database. | High | Rohini | 2019-06-04 | 2019-08-04 | 6 | M | Completed | The main objective is to fetch all the details from the database and view the candidate status and candidate result by fetching the details from the database using the requirement ID and interview ID. | HR will login to te interview observation form with the help of which candidate will be able to see his/her candidate status and candidate result. | Scrum Master | Average | High | New Requirement
|  |  |  | Task#15 | View the candidate status and candidate results details by fetching it from the database using the requirement id and interview id and displaying it on a new page | High | Prachi | 2019-08-04 | 2019-09-04 | 6 | L | Completed |  |  | Scrum Master | Average | High | New Requirement