## Sheet1
Requirements | Sprint | Topic | User Story | Task # | Task | Priority | Assigned To | Start Date | End Date | Hours[Task Based] Estimate the testing+development-Technical Panel | StoryPoint[Businessvalue/complexity] Estimates how much we can deliver in a spring+total effort with its tasks with its depencies and other factors[Po+scrum] | Status
| #1 | User Registration | As an user, I want to open user registration page and save the entered user details. | Task#1 | Create a Login JSP page to accept UserId and Password and allow to login and provide with registration link. | High | Prachi | 28/3/19 | 28/3/19 | 5 |  | Done
|  |  |  | Task#2 | Create a jsp pageand redirect to user Registration Page | High | Rohini | 28/3/19 | 29/3/19 | 11 |  | Done
|  |  |  | Task#3 | User Registration Field Validation | Medium | Prachi | 29/3/19 | 29/3/19 | 1 |  | Done
|  |  |  | Task#4 | Submit the data and store it in the database | High | Rohini | 29/3/19 | 29/3/19 | 3
|  |  |  | Task#5 | Create User Entity class, User DAO and User Service class to insert the admin data and controller and verify on backend. | High | Prachi | 29/3/19 | 30/3/19 | 3.5
|  |  |  | Task#6 | Successful login | High | Pranay | 29/3/19 | 30/3/19 | 0.5
| #2 | HR Home | As an HR, I want to land on HR Home page which will display all the HR Functionalities from the database | Task#7 | Create a jsp page for HR Home and successfully land on it after validating credentials. | High | Prachi | 31/03/19 | 31/03/19 | 3 |  | Done
|  |  |  | Task#8 | Fetch all the details from the database by creating candidate class, DAO, Service and controller | High | Rohini | 31/03/19 | 2019-01-04 | 11 |  | Done
|  |  |  | Task#9 | Create a ' Candidate requirement' and redirect to Add Candidate RequirementPage and submit the details in the database. | High | Rohini | 2019-02-04 | 2019-02-04 | 10 |  | Done
|  |  |  | Task#10 | Edit candidate details by updating it in the database using the requirement id . | High | Prachi | 2019-03-04 | 2019-04-04 | 13 |  | Done
|  |  |  | Task#11 | Schedule interview by redirecting to Schedule Interview Page. |  | Pranay | 2019-05-04 | 2019-06-04 | 9
|  |  |  | Task#12 | provide interview results of different candidates by redirecting it to Interview Observation page. | High | Rohini | 2019-06-04 | 2019-06-04 | 2 |  | Done
| #3 | Candidate Home | As an candidate, I want to land on Candidate Home page which will display all the details from the database | Task#13 | Create a jsp page for Candidate Home and successfully land on it after validating credentials. | High | Prachi | 2019-06-04 | 2019-06-04 | 2 |  | Done
|  |  |  | Task#14 | Fetch all the details from the database. | High | Rohini | 2019-06-04 | 2019-08-04 | 15 |  | Done
|  |  |  | Task#15 | View the candidate status and candidate results details by fetching it from the database using the requirement id and interview id and displaying it on a new page | High | Prachi | 2019-08-04 | 2019-09-04 | 15 |  | Done